**USM/NEASC 5-Year Interim Report**

**Due Dates TIMELINE**

NEASC Kick Off Meeting: January 30, 2015

Team Leader Meeting: May 18, 2015

Team Leader Meeting: June 22, 2015

Team Leader Meeting: July 27, 2015

Team Leader Meeting: September 14, 2015

Area of Emphasis 1st draft due: October 1, 2015

Reflective Essay 1st draft due: October 1, 2015

Standards Update 1st draft due: October 15, 2015

Team Leader Meeting: November 2, 2015

Areas of Emphasis 2nd draft due: November 2, 2015

Reflective Essay 2nd draft due: November 2, 2015

Standards Update 2nd draft due: November 2, 2015

Complete Report 1st draft to NEASC: December 1, 2015

Final Complete Report due to NEASC: January 15, 2016